## Dashboard
L&C Career Platform Project Tracker
Mission: Build a useful, student-centered career platform that strengthens the Career Center and Career Accelerator. Competition success is welcome, but student usefulness, privacy, accessibility, and long-term sustainability come first.
Project Health | Value |  | Project principles
Total tasks | 34 |  | 1 | Student-centered | Every feature must solve a real student problem.
Completed | 0 |  | 2 | Private by default | Students control sharing and access.
In progress | 0 |  | 3 | Support people, not replace them | Technology should improve advising and faculty support.
Not started | 30 |  | 4 | Accessible | Works across devices and for users with different needs.
Blocked | 0 |  | 5 | Sustainable | Simple enough to maintain after the competition.
Completion rate | 0% |  | 6 | Evidence-driven | Research and testing guide priorities.
Current recommended scope
Phase | Focus | Primary users | Key deliverables | Why now | Competition fit | Long-term value | Status
1 | Responsive web MVP | Students, Career Advisors, Admin | Experiences, skills, tasks, sharing, advisor view | Core foundation | Directly addresses challenge | High | Planned
2 | Faculty contributions | Students, Faculty Contributors | Career resources and research opportunities | Adds L&C-specific value | Innovation | High | Planned
3 | Recommendation requests | Students, Faculty | Structured request form, document sharing, reminders | Useful but privacy-sensitive | Optional bonus | Medium-High | Backlog
4 | Mobile app | Students | Quick updates and notifications using same API | Only after web usage is validated | Not needed initially | Medium | Later
Immediate next actions
# | Action | Owner | Area | Priority | Status | Due date | Reason
1 | Interview 5–8 students from different majors/class years | Daniel | Research | High | Not Started |  | Validate real problems before coding
2 | Meet with Career Center/Career Accelerator staff | Daniel | Research | High | Not Started |  | Understand workflows and data boundaries
3 | Finalize MVP requirements and non-goals | Daniel | Planning | High | Not Started |  | Prevent scope creep
4 | Create wireframes for student and advisor flows | Daniel | Design | High | Not Started |  | Test usability early
5 | Define database schema and access-control rules | Daniel | Backend | High | Not Started |  | Security must be designed early
6 | Build first end-to-end experience tracking flow | Daniel | Development | High | Not Started |  | Demonstrate real value quickly

## Roadmap
Development Roadmap and Task Tracker
ID | Phase | Workstream | Task | Deliverable / Definition of Done | Priority | Status | Owner | Target Date | Notes / Dependencies
R-01 | Discovery | Student research | Interview students across majors and class years | At least 5 interviews summarized with recurring needs and pain points | High | Not Started | Daniel |  | Include international students, athletes, first-years, and seniors
R-02 | Discovery | Staff research | Interview Career Center and Career Accelerator staff | Document current workflows, tools, bottlenecks, and desired outcomes | High | Not Started | Daniel |  | Clarify what should integrate with Handshake
R-03 | Discovery | Faculty research | Interview 2–3 faculty members | Validate resource-sharing and recommendation-letter ideas | Medium | Not Started | Daniel |  | Ask how much time they can realistically contribute
R-04 | Discovery | Privacy research | Identify institutional privacy and data-handling requirements | Written list of required controls and unresolved policy questions | High | Not Started | Daniel |  | Do not collect sensitive data without a clear purpose
P-01 | Planning | Product definition | Write problem statement and target outcomes | One-page product brief approved for use throughout project | High | Not Started | Daniel |  | Use student value as primary criterion
P-02 | Planning | Scope | Define MVP and non-goals | MVP list and deferred-feature list finalized | High | Not Started | Daniel |  | Recommendation letters and mobile app likely deferred
P-03 | Planning | Success metrics | Define success measures | Metrics for usability, engagement, advising value, and privacy confidence | Medium | Not Started | Daniel |  | Examples: task completion, return usage, student confidence
D-01 | Design | Information architecture | Map pages and navigation | Student, advisor, faculty, and admin site maps | High | Not Started | Daniel |  | Keep each role focused
D-02 | Design | Wireframes | Create student dashboard wireframe | Dashboard tested with at least 3 students | High | Not Started | Daniel |  | Show next action, experiences, skills, and privacy
D-03 | Design | Wireframes | Create Career Advisor dashboard wireframe | Advisor flow reviewed by Career Center staff | High | Not Started | Daniel |  | Only show authorized student data
D-04 | Design | Accessibility | Create accessibility checklist | Checklist covers keyboard, contrast, labels, focus states, mobile layout | High | Not Started | Daniel |  | Test throughout, not only at the end
B-01 | Backend | Architecture | Select backend stack and deployment approach | Architecture decision recorded | High | Not Started | Daniel |  | Recommended: FastAPI or NestJS + PostgreSQL + Docker
B-02 | Backend | Database | Design initial schema | ERD covers users, roles, experiences, skills, tasks, sharing, audit logs | High | Not Started | Daniel |  | Include ownership and timestamps on student data
B-03 | Backend | Authentication | Implement prototype authentication | Users can register/sign in securely in prototype | High | Not Started | Daniel |  | Plan for future L&C SSO
B-04 | Backend | Authorization | Implement role and record-level access | Backend checks ownership, role, consent, and purpose | High | Not Started | Daniel |  | Never enforce permissions only in frontend
B-05 | Backend | API | Build experience and skill APIs | Create/read/update/delete works with validation and tests | High | Not Started | Daniel |  | Use reusable API for future mobile app
B-06 | Backend | Privacy | Build sharing permissions and audit logging | Student can grant/revoke access; accesses are logged | High | Not Started | Daniel |  | Private by default
F-01 | Frontend | Foundation | Create responsive web application shell | Accessible navigation works on phone and desktop | High | Not Started | Daniel |  | Build website first
F-02 | Frontend | Student experience | Build experience tracker | Student can add, edit, filter, and reflect on experiences | High | Not Started | Daniel |  | Connect each experience to skills
F-03 | Frontend | Skills | Build skills evidence map | Each skill displays linked evidence | High | Not Started | Daniel |  | Avoid unsupported self-ratings without evidence
F-04 | Frontend | Career tasks | Build roadmap and next-action view | Student sees tasks and one recommended next step | High | Not Started | Daniel |  | Keep recommendations explainable
F-05 | Frontend | Networking | Build professional connection tracker | Student can record contacts and follow-up dates | Medium | Not Started | Daniel |  | Private notes should stay private
F-06 | Frontend | Advisor experience | Build authorized student summary | Advisor can view only shared/assigned information | High | Not Started | Daniel |  | Include clear access labels
F-07 | Frontend | Privacy | Build Privacy & Sharing page | Student can see, grant, and revoke access | High | Not Started | Daniel |  | Show who can access what
Q-01 | Testing | Usability | Test MVP with students | At least 5 users complete core tasks; issues prioritized | High | Not Started | Daniel |  | Observe behavior, do not only ask opinions
Q-02 | Testing | Staff validation | Test advisor workflow with staff | Staff feedback incorporated into next iteration | High | Not Started | Daniel |  | Measure whether it improves advising preparation
Q-03 | Testing | Security | Test access boundaries | Student A cannot access Student B; advisor restrictions verified | High | Not Started | Daniel |  | Add automated authorization tests
Q-04 | Testing | Accessibility | Run accessibility review | No critical keyboard, contrast, labeling, or focus issues | High | Not Started | Daniel |  | Document fixes
C-01 | Competition | Demo | Prepare end-to-end demo | Demo follows a student from experience entry to advisor-ready summary | Medium | Not Started | Daniel |  | Show usefulness, not just visual polish
C-02 | Competition | Submission | Map product to challenge criteria | Submission explains relevance, UX, technical work, innovation, accessibility | Medium | Not Started | Daniel |  | Do not distort product priorities for points
L-01 | Long-term | Faculty resources | Add faculty-contributed resources | Faculty can submit; Career staff can review and publish | Medium | Backlog | Daniel |  | Keep contribution under two minutes
L-02 | Long-term | Recommendations | Design recommendation-request workflow | Purpose-specific sharing, status tracking, reminders, document handling | Medium | Backlog | Daniel |  | Build after core privacy model is stable
L-03 | Long-term | Mobile | Evaluate mobile app need | Decision based on actual web usage and student feedback | Low | Backlog | Daniel |  | Reuse same backend API if built

## Roles & Access
Roles, Permissions, and Data Access
Role | Purpose | Can view | Can create/update | Cannot access by default | How access is granted | MVP? | Notes
Student | Own and direct career journey | Own profile, experiences, skills, contacts, tasks, shared resources | Own records and sharing choices | Other students' records; private advisor notes | Ownership after authenticated login | Yes | Can export and delete own data
Career Advisor | Guide students and improve advising | Assigned or consenting students' shared information | Advisor recommendations and assigned actions | Unshared contact notes, unrelated files, all-student browsing | Assignment plus student consent or approved institutional policy | Yes | Best student-facing name for advising staff
Career Content Manager | Organize and verify opportunities and resources | Faculty submissions and public career content | Publish, tag, update, archive content | Private student records unless separately authorized | Career Center staff role | Yes/Maybe | Could be combined with admin in prototype
Faculty Contributor | Share disciplinary expertise and respond to requests | Own resource posts; recommendation request materials explicitly shared | Own posts, research opportunities, request responses | Full student profile, networking database, other requests | Faculty account plus purpose-specific student sharing | Phase 2 | Two separate functions: contributor and recommender
System Administrator | Maintain technical system and role configuration | Account metadata, system settings, audit logs as authorized | Roles, configuration, categories | Routine browsing of private student content | Restricted institutional authorization | Yes | Technical power should not imply unrestricted content access
Developer / Support | Build and troubleshoot system | Mock or anonymized data by default | Code and non-production configuration | Real student data without temporary audited approval | Temporary, documented support access only | Yes | Separate development and production environments
Alumni / Employer Contributor | Future mentoring or opportunity contribution | Own approved contributions | Own posts or mentoring availability | Student records by default | Opt-in connection and moderation | Later | Not part of initial scope
Data access matrix
Data category | Student | Career Advisor | Faculty | Content Manager | System Admin | Developer | Default rule
Student profile | Own | With consent/assignment | Selected fields only | No | Limited account fields | No | Private
Experiences | Own CRUD | Shared/assigned view | Only selected records | No | Aggregated by default | Mock/anonymized | Private
Skills and evidence | Own CRUD | Shared/assigned view | Selected view | No | Aggregated by default | Mock/anonymized | Private
Networking contacts | Own CRUD | Only if explicitly shared | No | No | No routine access | No | Highly private
Private contact notes | Own only | Explicit item-level permission only | No | No | No routine access | No | Highly private
Career tasks/goals | Own CRUD | Shared/assigned view and recommendations | Selected view | No | Aggregated by default | Mock/anonymized | Private
Uploaded documents | Own | Shared documents only | Request-specific files only | No | No routine access | No | Private file storage
Faculty resources | View | View | Own submissions | Review/publish | Manage categories | Development copy | Institutional/public
Recommendation request | Own status/materials | No unless student shares | Specific request only | No | Technical metadata only | No | Purpose-limited
Audit logs | Own access history | Limited relevant history | No | No | Authorized security access | No by default | Restricted
Aggregated reports | Opt-in/anonymous contribution | Authorized use | No | Authorized use | Authorized use | Synthetic only | Minimum necessary

## Product Scope
Product Scope: MVP, Later, and Non-Goals
Feature | Problem solved | Primary user | MVP | Phase | Data sensitivity | Success signal | Notes
Experience tracker | Students forget or cannot explain what they have done | Student | Yes | 1 | Private | Students add and reuse experiences | Core feature
Skills evidence map | Students list skills without proof | Student, Advisor | Yes | 1 | Private | Skills link to real evidence | Core differentiator
Career tasks and next action | Students feel overwhelmed and do not know what to do next | Student, Advisor | Yes | 1 | Private | Students complete recommended actions | Keep recommendations transparent
Professional connection tracker | Students lose networking context and follow-ups | Student | Yes | 1 | Highly private | Students record and follow up with contacts | Private by default
Privacy & Sharing center | Students need control over their data | Student | Yes | 1 | Highly sensitive | Students understand and manage access | Must be backend-enforced
Career Advisor dashboard | Advisors need concise preparation context | Career Advisor | Yes | 1 | Private | Advising conversations become more focused | Only authorized data
Faculty resources | Opportunities and disciplinary knowledge are scattered | Faculty, Student, Career staff | Limited | 2 | Institutional/public | Useful posts stay current and discoverable | Career staff review content
Recommendation requests | Students provide incomplete context and miss deadlines | Student, Faculty | No | 2 | Sensitive documents | Clearer requests and fewer missed deadlines | Purpose-specific access
Mobile app | Students may need quick entry and reminders | Student | No | 4 | Same as web | Validated demand after web launch | Responsive site first
Handshake integration | Avoid duplicate opportunity systems | Student, Career staff | No | Later | Institutional | Approved integration adds value | Do not scrape or duplicate blindly
AI-generated decisions | Could create opaque or biased guidance | All | No | Non-goal | High risk | N/A | AI may assist writing later, never make hidden decisions

## Research & Testing
Research, Interviews, and Testing Log
ID | Type | Participant / Group | Perspective | Date | Main question | Key finding | Decision affected | Follow-up | Status
RT-01 | Student interview |  | First-year student |  | What makes career planning confusing early on? |  | Dashboard and onboarding |  | Planned
RT-02 | Student interview |  | Junior/senior student |  | Where do you currently track experiences, contacts, and applications? |  | Core workflow |  | Planned
RT-03 | Student interview |  | International student |  | What career information or deadlines are hardest to navigate? |  | Resources and privacy |  | Planned
RT-04 | Student interview |  | Student-athlete |  | What prevents you from using career services consistently? |  | Mobile/responsive design |  | Planned
RT-05 | Staff interview |  | Career Advisor |  | What information would improve advising preparation? |  | Advisor dashboard |  | Planned
RT-06 | Staff interview |  | Career Accelerator staff |  | Which student activities and outcomes should be tracked? |  | Success metrics |  | Planned
RT-07 | Faculty interview |  | Faculty Contributor |  | What career resources can faculty realistically share and maintain? |  | Faculty feature scope |  | Planned
RT-08 | Usability test |  | Student |  | Can the user add an experience and understand its skill evidence without help? |  | Experience flow |  | Planned
RT-09 | Security test |  | Test accounts |  | Can one user access another user's record by changing an ID? |  | Authorization |  | Planned
RT-10 | Accessibility test |  | Keyboard/screen-reader review |  | Can all core flows be completed without a mouse? |  | Accessibility |  | Planned

## Decision Log
Product and Technical Decision Log
Decision ID | Date | Decision | Reason | Alternatives considered | Evidence | Impact | Revisit when
DEC-001 | 2026-07-22 | Build a responsive website before a native mobile app | Faster delivery, one frontend, easier testing and maintenance | Web + native app together | Current project discussion | Keeps MVP realistic | Students demonstrate unmet mobile-only needs
DEC-002 | 2026-07-22 | Use a reusable backend API | Supports future mobile app and clean separation of concerns | Frontend connected directly to database | Security and scalability requirements | Stronger architecture | Only if platform constraints require another approach
DEC-003 | 2026-07-22 | Make student data private by default | Students should control access to personal career information | Broad staff access | Project values and privacy discussion | Requires record-level permissions | Institutional policy requires a clearly justified exception
DEC-004 | 2026-07-22 | Call direct student-support staff Career Advisors | Clear and familiar student-facing name | Career Center User, Staff | Role discussion | Better UX | Career Center prefers another official title
DEC-005 | 2026-07-22 | Include faculty resources before recommendation letters | Lower complexity and immediate institutional value | Build both in MVP | Scope discussion | Recommendation workflow moves to phase 2 | Core MVP is stable
DEC-006 | 2026-07-22 | Optimize for student usefulness, not only competition scoring | Primary mission is to help L&C students and strengthen the program | Competition-first feature selection | Project mission | Guides all prioritization | Never; this is a core principle

## Competition Alignment
Competition Alignment Without Losing the Mission
Challenge area / criterion | Our feature or evidence | Student benefit | Competition benefit | Risk of over-optimizing | Mitigation | Status
Experience tracking | Experience tracker with reflection and reusable evidence | Students remember and explain their growth | Strong problem relevance | Turning it into a complicated portfolio builder | Keep entry fast and test with students | Planned
Professional networking | Private contact and follow-up tracker | Students maintain relationships intentionally | Directly addresses challenge | Collecting too much sensitive information | Minimize fields and keep notes private | Planned
Skills development | Skills evidence map | Students connect claims to proof | Innovative connection between records | Artificial readiness scores | Use transparent evidence, not unexplained scoring | Planned
Career readiness | Tasks and one next action | Reduces overwhelm | Strong UX story | Gamification without real value | Tie tasks to Career Center guidance | Planned
User experience | Responsive, role-specific flows | Easy use across devices | Largest scoring category | Polishing before validating | Test low-fidelity designs first | Planned
Technical execution | Backend API, PostgreSQL, role/access checks | Reliable and extensible system | Demonstrates full-stack ability | Building infrastructure nobody needs | Build only what core workflows require | Planned
Innovation | Faculty resources and connected evidence | Uses L&C community strengths | Distinctive concept | Adding features only to look novel | Require a validated student or staff need | Planned
Accessibility | Keyboard, contrast, labels, focus, mobile layout | More students can use the system | Protects accessibility points | Treating accessibility as final checklist | Test throughout development | Planned